Action Item Status (18 March 2019)

(updates anticipated at next meeting for Item #s highlighted in green)

| # | Start Date Closed Date | Action Item Description | OPI | Status/Comment Comment, Pending. Status, etc |
| --- | --- | --- | --- | --- |
| 1804 | 10 Sep 18 | Develop options, with estimates, for 50HP outboard motor for the zodiac and/or replacement for the Boston Whaler for inclusion in the 2019 budget | Chair, Boats | ONGOING. Looking at broader options for safety boat replacement |
| 1807 | 10 Sep 18 | Develop a Financial Policy and Procedures statement for the Branch. Present at October BoD meeting | Treasurer | PENDING. Treasurer looking to simplify. Will be in effect for 2019 |
| 1811 | 15 Oct 18 | Invite the CMUC leaders to the ACRs in the Spring (by next Tag Day?) (suggest this could be a broader action item for ACRs– if one at all) | VP SC & VP NL | DEFERRED - to be done as part of ACR planning |
| 1814 | 12 Nov 18 | Present option for way ahead on SC Medal Mounting Costs (if to be a budget consideration) for Board decision at Dec meeting | VP SC | PENDING |
| 1817 | 12 Nov 18 | Conduct Inventory Review through Nov/Dec with goal of required submission to NL Ont Div being ready by Jan 2019 | Treasurer | Not yet started. |
| 1819 | 12 Nov 18 | Script Supervisor pre-departure presentation & improve guidance in TAG pack for next TAG DAY (by Apr 2019) | Gerry Powell | DEFERRED - to be done with TAG Day Planning |
| 1824 | 10 Dec 18 | Draft of Membership Drive letter(s) for campaign to start in Jan | Treasurer | PENDING |
| 1825 | 10 Dec 18 | Updated - Presentation of 2017Bursaries | S&A Chair | 2018 bursaries done. 2017 pair to be mailed |
| 1901 | 14 Jan 19 | Review of bus contracting | COs, Treasurer | Treasurer to provide list of bus orders in 2018 for comparison |
|  | Upcoming Action Items | Final requirements for Spring Tag Days (Mar Meeting) (incl 1819) Brief on plan for NLC end of year Trip (April or May Meeting) Board discussion on Branch ACRs involvement (May meeting) |  |  |

Closed Action Items

| # | Start Date Closed Date | Action Item Description | OPI | Status/Comment Comment, Pending. Status, etc |
| --- | --- | --- | --- | --- |
| 1802 | 10 Sep 18 15 Oct 18 | Resolve space allocation issues at CFRB Dow’s Lake with XO CARLETON. VP SC to advise Board of the way ahead at next meeting | CO KINGSMILLL | Done. Talks will continue as year progresses |
| 1805 | 10 Sep 18 15 Oct 18 | Meet with the respective VPs & COs during Sept to review spending needs for the remainder of the year - update budget | Treasurer | Funding expectations for 2018 more realistic. See budget Mod 5. |
| 1801 | 10 Sep 18 12 Nov 18 | Rectify all of the claims (LSA/GSA) returned by DND for additional work by the end of Sept | CO FALKLAND | All re-submitted – work ongoing with a couple (receipt issues) |
| 1806 | 10 Sep 18 12 Nov 18 | Discuss with VP SC and CO FALKLAND options to better manage and track FALKLAND claims (if Branch advances are involved) to DND | Treasurer | Budget Mod 5A approved. Internal tracking process in effect. DND DFTs functioning. |
| 1812 | 15 Oct 18 | Investigate prop guard Requirement for HOWARD& provision by the NLC | President | 10 Dec 18 – not req for inboard motor. |
| 1813 | 15 Oct 18 | Obtain a quote to relocate muffler (exhaust?) on the HOWARD | Boats Chair | Will be addressed with item 1803 |
| 1815 | 12 Nov 18 10 Dec 18 | Complete order for NLC Parkas from Logistik Uniorps | CO KINGSMILL | Order in. Not expected until Mar 2019. Invoice will be paid then |
| 1816 | 12 Nov 18 10 Dec 18 | Prepare draft 2019 budget for Board consideration at Dec meeting | Treasurer | Done as best possible in absence of discussion on item 1809 and HOWARD work estimates. 2019 budget discussions to follow in Jan |
| 1818 | 12 Nov 18 | Update DROPBOX and LINKS to it | Treasurer | Done |
| 1809 | 15 Oct 18 OBE Jan 19 | Finalize “Mod 5 to the Budget – Exec to consolidate proposals for spending to the end of this year and advise Board at Nov meeting | Treasurer President |  |
| 1808 | 10 Sep 18 14 Jan 19 | Liaise with Corps COs and TAG DAY Chair to determine suitable dates for our TAG DAYS next Spring for Board decision at the Oct Meeting | VP SC VP NLC | 6 Apr conflict with Div AGM accepted |
| 1820 | 12 Nov 18 14 Jan 19 | Complete arrangements with RONA for new Discount Cards (TAG DAY) | TAG Chair | New cards ready for next TAG DAY |
| 1821 | 10 Dec 18 14 Jan 19 | Find Branch copy of MOU with Carleton in Treasurer’s records | Treasurer | Treasurer does not have a copy. Location of original unresolved, but President has a copy. |
| 1822 | 10 Dec 18 | Branch Commitment (March Break trip) Letter to RCSU | VP SC |  |
| 1823 | 10 Dec 18 14 Jan 19 | Obtain cost estimate for NLC end-of-year trip for budget plan | VP NLC |  |
| 1803 | 10 Sep 18 Sec - Jan 19 | Develop list of work needed on the HOWARD and obtain estimates for consideration by the Board towards the 2019 budget | Chair, Boats | Work required and cost estimate approved secretarially in Jan |
| 1810 | 15 Oct 18 11 Feb 19 | Prepare NL104 Community Service Award signed by National President for presentation to CMUC | Jim Cummings | PENDING. |